## NECommon Changes
Change Number | Version Number | Date | Schema | Complex Type Name | Requested Action | Requested By | Status | Comments
1 | 2009V1.1 | 2009-09-18 | NEeFileTypes | n/a | Change included file from efileTypes.xsd to StateeFileTypes.xsd | Sean Murphy, Jackson Hewitt Technology | Done | A number of the elements in NEeFileTypes.xsd refer to TIGERS elements in StateeFileTypes.xsd; the file formerly included the IRS efileTypes.xsd but not the broader TIGERS file. We've modified the include statement to use the TIGERS file instead.
2 | 2009V1.1 | 2009-09-18 | NEeFileTypes | n/a | Add type="CheckboxType" as an attribute to Resident and Nonresident elements; added a "fixed" attribute forcing value to be checked if the user selects either of those types. | Sean Murphy, Jackson Hewitt Technology | Done | The previous version had these as empty elements; however some parsers need a type attribute to validate correctly. We made it fixed so that selection of either of these elements automatically marks the field as checked.
3 | 2009V1.1 | 2009-09-18 | NEeFileTypes | n/a | Add type="PersonNameType" as an attribute to CareProviderPersonName element; Add type="BusinessNameType" as an attribute to CareProviderBusinessName | Sean Murphy, Jackson Hewitt Technology | Done | This was what was intended in the first place; not only did I miss adding the type attributes, but I also wrote the sample applications to fit the incorrect structure. (In particular, both of the sample files had CareProviderBusinessName elements without a required BusinessNameLine1 subelement.) Sample files have been changed to match the corrected structure.
4 | 2009V1.3 | 2009-10-26 | NEeFileTypes | n/a | Renamed "EVerifyComplianceType" to "NeEVerifyComplianceType" to clarify that it is a Nebraska type as opposed to a TIGERS type. | TIGERS | Done | Requested in an e-mail from Jacob Dubreuil at TIGERS, dated 10/26/2009
5 | 2009V1.3 | 2009-10-26 | NEeFileTypes | n/a | Renamed "EVerifyType" to "NeEVerifyType" to clarify that it is a Nebraska type as opposed to a TIGERS type. | TIGERS | Done | Requested in an e-mail from Jacob Dubreuil at TIGERS, dated 10/26/2009
6 | 2009V1.3 | 2009-10-26 | NEFinancialTransaction | n/a | Moved from the Common folder, to clarify that it is a restriction of the TIGERS FinancialTransaction type | TIGERS | Done | Requested in an e-mail from Jacob Dubreuil at TIGERS, dated 10/26/2009
7 | 2009V1.5 | 2010-09-08 | NEeFileTypes | NeF1040nTypeOfReturnType | Changed NeF1040nTypeOfReturnType to use type="CheckboxType" fixed="X" for elements Resident and Nonresident. | Nebraska - Internal Form changes |  | This change resulted from a question from a software developer and the subsequent decision to include this Type definition.
8 | 2009V1.5 | 2010-09-08 | NEeFileTypes | NeF1040nTaxAfterNonrefCrType | Renamed "NETaxLessRefundableCredits" to "NETaxLessNonrefundableCredits" to clarify that it is a subtraction of 1040N non-refundable credits (lines 19-25), not refundable credits (lines 28-33). | Nebraska - Internal Form changes |  | This change resulted from an internal review of V1.5.
9 | 2009V1.5 | 2010-09-08 | NEeFileTypes | NeF1040nTaxAfterNonrefCrType | Made element TotalFederalTax required (minOccurs="1") | Nebraska - Internal Form changes |  | This data was determined to be required in the schema.
10 | 2009V1.5 | 2010-09-08 | NEeFileTypes | NeF1040nTaxAfterNonrefCrType | Made element NETaxLessNonrefundableCredits required (minOccurs="1") | Nebraska - Internal Form changes |  | This data was determined to be required in the schema.
11 | 2009V1.5 | 2010-09-08 | NEeFileTypes | NeF1040nTaxAfterNonrefCrType | Added Boolean Checkbox to indicate when the taxpayer is entering federal tax because it is less than the computed Nebraska tax. This makes this complex type conform to the format of the form line. | Nebraska - Internal Form changes |  | This change resulted from a request by processing staff.
12 | 2009V1.5 | 2010-09-08 | NEeFileTypes | NeF1040nTaxAfterNonrefCrType | Changed Form Line references from line 28 to line 27. | Nebraska - Internal Form changes |  | This change was a result of form line renumbering.
13 | 2009V1.5 | 2010-09-08 | NEeFileTypes | NeForm1040nFedTaxLinesType | Changed Form Line references from line 28 to line 27. | Nebraska - Internal Form changes |  | This change was a result of form line renumbering.
14 | 2009V1.5 | 2010-09-08 | NEeFileTypes | NeF1040nEarnedIncomeCreditType | Changed Form Line references from line 34 to line 33. | Nebraska - Internal Form changes |  | This change was a result of form line renumbering.
15 | 2009V1.5 | 2010-09-08 | NEeFileTypes | NeF1040nConsumersUseTaxType | Added new complex type for worksheet lines to compute Form 1040N Line 37 Consumers Use Tax. | Nebraska - Internal Form changes |  | This change was a result of annual form changes.
16 | 2009V1.5 | 2010-09-08 | NEeFileTypes | NeS3PartYrCreditsType | Removed element S3CharitableEndowCredit from list of part year resident credits in the complex type for Schedule III Line 71. | Nebraska - Internal Form changes |  | This change was a result of annual form changes.
17 | 2009V1.5 | 2010-09-08 | NEeFileTypes | NeF3800nDistrCreditsRecvedType | Changed element YearCreditEarned from DateType to YearType | Nebraska - Internal Form changes |  | This corrects a schema design error.
18 | 2009V1.5 | 2010-09-08 | NEeFileTypes | NeF3800nIncentCredDistrType | Changed element YearCreditEarned from DateType to YearType | Nebraska - Internal Form changes |  | This corrects a schema design error.
19 | 2009V1.5 | 2010-09-08 | NEeFileTypes | NeMicroentColumnAType | Changed element ColumnATaxYearEndDate from YearType to DateType. | Nebraska - Internal Form changes |  | This corrects a schema design error.
20 | 2009V1.5 | 2010-09-08 | NEeFileTypes | NeMicroentColumnBType | Changed element ColumnBTaxYearEndDate from YearType to DateType. | Nebraska - Internal Form changes |  | This corrects a schema design error.
21 | 2010V1.1 | 2010-12-10 | NEeFileTypes | NeF1040nTypeOfReturnType | Enhanced this complex type to change how element PartialYearResident is reported. | Nebraska - Internal Form changes |  | This corrects a schema design error.
22 | 2011V1.0 | 2011-09-20 | NEeFileTypes | NeF3800nDistrCreditRecvdType | Added new complex type for Form 3800N Line 15 Distributed Credits Received. | Nebraska - Internal Form changes |  | This change was a result of annual form changes.
23 | 2011V1.0 | 2011-09-20 | IndividualStateEnumerations | NeTypeOfBusinessType | Added new string values "Resident Individual", "Nonresident Indvidual" and "Other". | Nebraska - Internal Form changes |  | This change was due to a form change to support Form K-1N.
24 | 2011V1.0 | 2011-09-20 | NEeFileTypes | NeS1InterestIncomeType | Changed element TotalStateAndLocalInteres maxOccurs value from unbounded to 1000. | Nebraska - Internal Form changes |  | This change was a result of an internal schema review.
25 | 2011V1.0 | 2011-09-20 | NEeFileTypes | NeS1InterestIncomeType | Changed element NebraskaStateAndLocalInterest maxOccurs value from unbounded to 1000. | Nebraska - Internal Form changes |  | This change was a result of an internal schema review.
26 | 2011V1.0 | 2011-09-20 | NEeFileTypes | NeS1USGovtObligationsType | Changed element InterestAndDividendIncome maxOccurs value from unbounded to 1000. | Nebraska - Internal Form changes |  | This change was a result of an internal schema review.
27 | 2011V1.0 | 2011-09-20 | NEeFileTypes | NeS1USGovtObligationsType | Changed element RegulatedInvCoDividends maxOccurs value from unbounded to 1000. | Nebraska - Internal Form changes |  | This change was a result of an internal schema review.
28 | 2011V1.0 | 2011-09-20 | NEeFileTypes | NeS1TierIOrIIBenefitsType | Changed element TaxableTierRRBenefits maxOccurs value from unbounded to 1000. | Nebraska - Internal Form changes |  | This change was a result of an internal schema review.
29 | 2011V1.0 | 2011-09-20 | NEeFileTypes | NeFCDNCreditsReceivedType | Changed element ReceiverPerson type value from PersonType to NePersonType. | Nebraska - RSI recommendation |  | This change was a result of an external schema review.
30 | 2011V1.0 | 2011-09-20 | NEeFileTypes | NeF3800nIncentCredDistrType | Changed element PersonData type value from PersonType to NePersonType. | Nebraska - RSI recommendation |  | This change was a result of an external schema review.
31 | 2011V1.0 | 2011-09-20 | NEeFileTypes | NeF3800nIncentCredDistrType | Changed element PersonData type value from BusinessType to NeBusinessType. | Nebraska - RSI recommendation |  | This change was a result of an external schema review.
32 | 2011V1.0 | 2011-09-20 | NEeFileTypes | NeF3800nDistribRDCreditType | Changed element ReceiverName type value from PersonType to NePersonType. | Nebraska - RSI recommendation |  | This change was a result of an external schema review.
33 | 2011V1.0 | 2011-09-20 | NEeFileTypes | NeF4797nPartIIType | Changed element NameSsnOfPersMakingElection type value from PersonType to NePersonType. | Nebraska - RSI recommendation |  | This change was a result of an external schema review.
34 | 2011V1.0 | 2011-09-20 | NEeFileTypes | NePersonOrBusinessType | Added new complex type for Nebraska person or business choice gate. | Nebraska - RSI recommendation |  | This change was a result of an external schema review.
35 | 2011V1.0 | 2011-09-20 | NEeFileTypes | NePersonType | Added new complex type for Nebraska person type. | Nebraska - RSI recommendation |  | This change was a result of an external schema review.
36 | 2011V1.0 | 2011-09-20 | NEeFileTypes | NeBusinessType | Added new complex type for Nebraska business type. | Nebraska - RSI recommendation |  | This change was a result of an external schema review.
37 | 2012V1.0 | 2012-02-27 | IndividualStateEnumerations | NeTypeOfIncentiveProgramType | Added enumeration value "Nebraska Advantage Act (LB 312)" | Nebraska - correction |  | This change was a result of developer comments.
38 | 2012V1.0 | 2012-06-11 | NEeFileTypes | NeF4797nElectionDecisionType | Removed element NeF4797nElectionDecisionType | Obsolete and not supported |  | Result of an internal schema review. Because it was never supported, this is still backwards compatible.
39 | 2012V1.0 | 2012-06-11 | NEeFileTypes | NeF4797nMadeElectionType | Removed element NeF4797nMadeElectionType | Obsolete and not supported |  | Result of an internal schema review. Because it was never supported, this is still backwards compatible.
40 | 2012V1.0 | 2012-06-11 | NEeFileTypes | NeF4797nElectNotMadeType | Removed element NeF4797nElectNotMadeType | Obsolete and not supported |  | Result of an internal schema review. Because it was never supported, this is still backwards compatible.
41 | 2012V1.0 | 2012-06-11 | NEeFileTypes | NeF4797nPartIIType | Removed element NeF4797nPartIIType | Obsolete and not supported |  | Result of an internal schema review. Because it was never supported, this is still backwards compatible.
42 | 2012V1.0 | 2012-06-11 | NEeFileTypes | NeF4797nEmployeeType | Removed element NeF4797nEmployeeType | Obsolete and not supported |  | Result of an internal schema review. Because it was never supported, this is still backwards compatible.
43 | 2012V1.0 | 2012-06-11 | NEeFileTypes | NeF4797nSurvSpouseType | Removed element NeF4797nSurvSpouseType | Obsolete and not supported |  | Result of an internal schema review. Because it was never supported, this is still backwards compatible.
44 | 2012V1.0 | 2012-06-11 | NEeFileTypes | NeF4797nOldestIssueType | Removed element NeF4797nOldestIssueType | Obsolete and not supported |  | Result of an internal schema review. Because it was never supported, this is still backwards compatible.
45 | 2012V1.0 | 2012-06-11 | NEeFileTypes | NeF4797nPartIType | Removed element NeF4797nPartIType | Obsolete and not supported |  | Result of an internal schema review. Because it was never supported, this is still backwards compatible.
46 | 2012V1.0 | 2012-06-11 | NEeFileTypes | NeF4797nPartIIIType | Removed element NeF4797nPartIIIType | Obsolete and not supported |  | Result of an internal schema review. Because it was never supported, this is still backwards compatible.
47 | 2012V1.0 | 2012-06-11 | NEeFileTypes | NeF4797nP1NoPubTradedType | Removed element NeF4797nP1NoPubTradedType | Obsolete and not supported |  | Result of an internal schema review. Because it was never supported, this is still backwards compatible.
48 | 2012V1.0 | 2012-06-11 | NEeFileTypes | NeF4797nPart2SaleOfStockType | Removed element NeF4797nPart2SaleOfStockType | Obsolete and not supported |  | Result of an internal schema review. Because it was never supported, this is still backwards compatible.
49 | 2012V1.0 | 2012-06-11 | NEeFileTypes | NeF4797nPart2ExclusionType | Removed element NeF4797nPart2ExclusionType | Obsolete and not supported |  | Result of an internal schema review. Because it was never supported, this is still backwards compatible.
50 | 2012V1.0 | 2012-06-11 | NEeFileTypes | EnhancedResearchCredMultBy35Pct | Renamed this element to EnhanceResearchCredMultBy35Pct to meet 30 character limit. | Nebraska - correction |  | This change was a result of an internal schema review.
51 | 2012V1.0 | 2012-06-11 | NEeFileTypes | OffAndOnCampusDecimalType | Renamed this element to NeOffAndOnCampusDecimalType to meet naming rules. | Nebraska - correction |  | This change was a result of an internal schema review.
52 | 2012V1.0 | 2012-06-11 | NEeFileTypes | OffAndOnCampusUSAmountNNType | Renamed this element to NeOffAndOnCampusUSAmountNNType to meet naming rules. | Nebraska - correction |  | This change was a result of an internal schema review.
53 | 2012V1.0 | 2012-06-11 | NEeFileTypes | ShareholderEntityType | Renamed this element to NeShareholderEntityType to meet naming requirements. | Nebraska - correction |  | This change was a result of an internal schema review.
54 | 2012V1.0 | 2012-06-11 | NEeFileTypes | AltMinTax | Renamed this element to AltMinTax1040NWks in NEeFileTypes.xsd for Nebraska Form 1040N Minimum or Other Tax Type to give it a unique element name. | Nebraska - correction |  | This change was a result of developer comments and requests.
55 | 2012V1.0 | 2012-09-17 | NEeFileTypes | NeF1040nEarnedIncomeCreditType | Removed element NebraskaEarnedIncomeCredit to eliminate redundancy | Nebraska - correction |  | This change was a result of developer comments and requests.
56 | 2012V1.0 | 2012-09-17 | NEeFileTypes | NeF1040nOtherTaxesPaidType | Removed element CreditForOtherTaxPaid to eliminate redundancy | Nebraska - correction |  | This change was a result of developer comments and requests.
57 | 2012V1.0 | 2012-09-17 | NEeFileTypes | NeS1InterestIncomeType | Removed element TotalInterestIncome to eliminate redundancy | Nebraska - correction |  | This change was a result of developer comments and requests.
58 | 2012V1.0 | 2012-09-17 | NEeFileTypes | NeS1LongTermCareRecapType | No longer using Complex Type NeS1LongTermCareRecapType | Nebraska - correction |  | This change was a result of developer comments and requests.
59 | 2012V1.0 | 2012-09-17 | NEeFileTypes | NeS1USGovtObligationsType | Removed element TotalInterestAndDividendIncome to eliminate redundancy | Nebraska - correction |  | This change was a result of developer comments and requests.
60 | 2012V1.0 | 2012-09-17 | NEeFileTypes | NeS1OtherAdjDecreasingType | Removed element TotalOtherAdjustDecreasingAGI to eliminate redundancy | Nebraska - correction |  | This change was a result of developer comments and requests.
61 | 2012V1.0 | 2012-09-17 | NEeFileTypes | NeS1TierIOrIIBenefitsType | Removed element TotalTierITierIIBenefits to eliminate redundancy | Nebraska - correction |  | This change was a result of developer comments and requests.
62 | 2012V1.0 | 2012-09-17 | NEeFileTypes | NeS3ComputedNebraskaTaxType | Removed element CalcNonresPartYrResTax to eliminate redundancy | Nebraska - correction |  | This change was a result of developer comments and requests.
63 | 2012V1.0 | 2012-09-17 | NEeFileTypes | NeS3MinimumOrOtherTaxType | Removed element NeShareMinTaxLessPEC to eliminate redundancy | Nebraska - correction |  | This change was a result of developer comments and requests.
64 | 2012V1.0 | 2012-09-17 | NEFinancialTransaction | EstimatedPayments | Added EstimatedPayments elements to schema to allow filers to set up estimated payments through MeF. | Nebraska - enhancement |  | This change was a Department intitiated enhancement.
65 | 2012V1.0 | 2012-09-17 | BinaryAttachment | BinaryAttachment | Added BinaryAttachment elements to schema to allow filers to submit PDF documents with the return. | Nebraska - enhancement |  | This change was a Department intitiated enhancement.
66 | 2012V1.0 | 2012-10-16 | NEeFileTypes | NeF2441nCareProviderGrpType | Added choice gate option for Tax Exempt to match federal | Developer request |  | This change was a result of developer comments and requests.
67 | 2012V1.0 | 2012-10-16 | NEeFileTypes | NeF1310nOthClaimRefDeceasType | Changed Checkbox Types and Boolean Types to meet best practices recommendations | Nebraska - RSI recommendation |  | This change was a result of an external schema review.
68 | 2012V1.0 | 2012-10-16 | IndividualStateEnumerations | NeTypeOfNeTaxReturnType | Removed enumerated list for type of return filed and replaced it with ReturnTypeType used with forms CDN and 3800N.. | Nebraska - RSI recommendation |  | This change was a result of an external schema review.
69 | 2012V1.2 | 2012-11-20 | NEeFileTypes | NeF2441nCareProviderGrpType | Corrected fixed value for Tax Exempt choice | Nebraska - correction |  | This change was a result of developer comments and requests.
70 | 2013V1.0 | 2013-08-20 | IndividualStateEnumerations | NeTypeOfIncentiveProgramType | Removed enumeration value "Nebraska Advantage Microenterprise Tax Credit Act" | Nebraska - correction |  | This change was a result of an internal schema review.
71 | 2013V1.0 | 2013-08-20 | IndividualStateEnumerations | NeRRBBenefitsDocumentationType | Added new enumerated list for type of RRB documentation allowed in support of Railroad Retirement Benefits claimed on Nebraska Schedule I. | Nebraska - enhancement |  | This change was a result of an internal schema review.
72 | 2013V1.0 | 2013-08-20 | IndividualStateEnumerations | NeTypeOfReturnType | Added new enumerated list for Nebraska Form 1040N Type of Residency; 1=Resident, 2=Part Yr. Res., 3= Nonresident. | Nebraska - enhancement |  | This change was a result of an internal schema review.
73 | 2013V1.0 | 2013-08-20 | IndividualStateEnumerations | NeFilingStatusType | Added new enumerated list for Nebraska Form 1040N Filing Status. Values are 1, 2, 3, 4 or 5. | Nebraska - enhancement |  | This change was a result of an internal schema review.
74 | 2013V1.0 | 2013-08-20 | IndividualStateEnumerations | NeEICNumberQualChildrenType | Added new enumerated list for Number of Qualifying Children From Federal Schedule EIC. Values are 0, 1, 2. or 3. | Nebraska - enhancement |  | This change was a result of an internal schema review.
75 | 2013V1.0 | 2013-08-20 | NEeFileTypes | NeF1040nTypeOfReturnType | This complex type has been restructured. This e-file type now references the enumerated list NeTypeOfReturnType for the TypeOfReturnDescription element. | Nebraska - enhancement |  | This change was a result of an internal schema review.
76 | 2013V1.0 | 2013-08-20 | NEeFileTypes | NeF1040nMinOthTaxType | Element AltMinTax1040NWks has been removed from this worksheet complex type. Other lines have been renumbered 16a through 16d. | Nebraska - enhancement |  | This change was a result of an internal schema review.
77 | 2013V1.0 | 2013-08-20 | NEeFileTypes | NeF1040nTaxAfterNonrefCrType | This complex type has been expanded and restructured. This is used to compute Nebraska tax on Form 1040N. It now contains all parts necessary to compute tax. | Nebraska - enhancement |  | This change was a result of an internal schema review.
78 | 2013V1.0 | 2013-08-20 | NEeFileTypes | NeF1040nEarnedIncomeCreditType | This complex type has been restructured. This e-file type now references the enumerated list NeEICNumberQualChildrenType for the EICNumberOfChildren element. | Nebraska - enhancement |  | This change was a result of an internal schema review.
79 | 2013V1.0 | 2013-08-20 | NEeFileTypes | NeF1040nConsumersUseTaxType | This complex type has been restructured to include a new sub-line for capturing purchases subject to local use tax on Form 1040N line 38. Previously, only purchases subject to state use tax was captured. The sub-lines have been renumbered, 91 through 95. | Nebraska - enhancement |  | This change was a result of a change in data requirements.
80 | 2013V1.0 | 2013-08-20 | NEeFileTypes | NeF1040nLocalConUseTaxType | This complex type is used to capture local use tax data and is required if local use tax is reported. This allows for schema enforcement of data collection and removes now unnecessary business rules. | Nebraska - enhancement |  | This change was a result of a change in data requirements.
81 | 2013V1.0 | 2013-08-20 | NEeFileTypes | NeS1InterestIncomeType | Nebraska Schedule I has undergone an extensive restructuring. What previously was line 45a and 45b under line 45 is now lines 45, 46 and 47. This complex type was used in prior years to capture lines 45a and 45b, but is no longer needed since these lines have been broken out. The new structure uses the USItemizedEntryType and separate total elements on SchI.xsd for lines 45, 46 and 47. | Nebraska - enhancement |  | This change was a result of a form change.
82 | 2013V1.0 | 2013-08-20 | NEeFileTypes | NeS1USGovtObligationsType | Nebraska Schedule I has undergone an extensive restructuring. What previously was lines 52a and 52b under line 52 is now lines 55, 56 and 57. This complex type was used in prior years to capture lines 52a and 52b, but is no longer needed since these lines have been broken out. The new structure uses the USItemizedEntryType for line 55 and now uses a revised separate complex type (see below) for line 56 data. | Nebraska - enhancement |  | This change was a result of a form change.
83 | 2013V1.0 | 2013-08-20 | NEeFileTypes | NeS1RegInvestCoDividendType | This complex type has been modified to remove what was previously Schedule I line 52a (now line 55) and now captures only what previously was line 52b data (now line 56). | Nebraska - enhancement |  | This change was a result of a form change.
84 | 2013V1.0 | 2013-08-20 | NEeFileTypes | NeS1RRBBenefitsType | This is a new complex type for capturing data for Schedule I Part B Taxable Benefits Paid by the Railroad Retirement Board. This e-file type references the enumerated list NeRRBBenefitsDocumentationType for the TypeOfRRBDocument element. | Nebraska - enhancement |  | This change was a result of a change in data requirements.
85 | 2013V1.0 | 2013-08-20 | NEeFileTypes | NeS1OtherAdjDecreasingType | This complex type is no longer used. Nebraska Schedule I has undergone an extensive restructuring. What previously was lines 57a through and 57h under line 57 is now lines 63 through 70 in SchI.xsd. This complex type is no longer needed since these lines have been broken out. | Nebraska - enhancement |  | This change was a result of a form change.
86 | 2013V1.0 | 2013-08-20 | NEeFileTypes | NeS3ComputedNebraskaTaxType | This complex type has been modified to add elements to capture all needed fields in the tax calculation. A subtotal (line 82c) has been added for the sum of lines 82a and 82b. | Nebraska - enhancement |  | This change was a result of a form change.
87 | 2013V1.0 | 2013-08-20 | NEeFileTypes | NeS3PartYrCreditsType | This complex type has been modified to add an element to capture the total of reported credits. A subtotal (line 82e) has been added for the sum of possible values reported in line 82d for Part Year Residents. This subtotal is then used to compute line 82. | Nebraska - enhancement |  | This change was a result of a form change.
88 | 2013V1.0 | 2013-08-20 | NEeFileTypes | NeS3MinimumOrOtherTaxType | Element AltMinTax1040NWks has been removed from this worksheet complex type and has been replaced by element SubtotalMultipliedBy296. Other lines have been renumbered 86a through 86g. | Nebraska - enhancement |  | This change was a result of a form change.
89 | 2013V1.0 | 2013-08-20 | NEeFileTypes | NeS3EarnedIncomeCreditType | This complex type was modified to remove elements FederalEICSubtotal and NebraskaEarnedIncomeCredit. These values have been moved to the SchIII.xsd. Also added new enumerated list for Number of Qualifying Children From Federal Schedule EIC. Values are 0, 1, 2. or 3. | Nebraska - enhancement |  | This change was a result of an internal schema review.
90 | 2014V1.0 | 2014-06-12 | NEeFileTypes | NeACHEntityDetailType | Created a new Nebraska version of complex type ACHEntittyDetailType used in Financial Transaction to make State Payment Date required. | Nebraska - enhancement | Done | This change was a result of an internal schema review.
91 | 2014V1.0 | 2014-07-22 | NEeFileTypes | NeF1040nOthTaxType | Renamed complex type NeF1040nMinOthTaxType to NeF1040nOthTaxType due to elimination of Alternative Minimum Tax. | Nebraska - form change | Done | This change was a result of the legislative change to remove alt min tax.
| 2014V1.0 | 2014-07-22 | NEeFileTypes | NeF1040nOthTaxType | Renamed element name Fed4972LumpSumDistributions to Fed4972LumpSumDistributionsAmt | Nebraska - standards update | Done | This was a change to meet new naming standards because the complex type was being updated anyway.
| 2014V1.0 | 2014-07-22 | NEeFileTypes | NeF1040nOthTaxType | Renamed element name Fed5329EarlyDistributions to Fed5329EarlyDistributionsAmt | Nebraska - standards update | Done | This was a change to meet new naming standards because the complex type was being updated anyway.
| 2014V1.0 | 2014-07-22 | NEeFileTypes | NeF1040nOthTaxType | Renamed element name OtherTaxSubtotal to OtherTaxSubtotalAmt | Nebraska - standards update | Done | This was a change to meet new naming standards because the complex type was being updated anyway.
93 | 2014V1.0 | 2014-07-23 | NEeFileTypes | NES3OtherTaxType | Renamed complex type NeS3MinimumOrOtherTaxType to NES3OtherTaxType due to elimination of Aternative Minimum Tax. | Nebraska - form change | Done
94 | 2014V1.0 | 2014-07-23 | NEeFileTypes | NeS3OtherTaxType | Renamed element AltMinTaxWrkshtTotal to OtherTaxWrkshtTotalAmt | Nebraska - standards update | Done | This was a change to meet new naming standards because the complex type was being updated anyway.
95 | 2014V1.0 | 2014-07-23 | NEeFileTypes | NeS3OtherTaxType | Renamed element OtherTaxWrkshtTotal to OtherTaxWrkshtTotalAmt | Nebraska - standards update | Done | This was a change to meet new naming standards because the complex type was being updated anyway.
96 | 2014V1.0 | 2014-07-23 | NEeFileTypes | NeS3OtherTaxType | Renamed element UnusedPEC to UnusedPECAmt | Nebraska - standards update | Done | This was a change to meet new naming standards because the complex type was being updated anyway.
97 | 2014V1.0 | 2014-07-23 | NEeFileTypes | NeS3OtherTaxType | Renamed element OtherTaxLessPEC to OtherTaxLessPECAmt | Nebraska - standards update | Done | This was a change to meet new naming standards because the complex type was being updated anyway.
98 | 2014V1.0 | 2014-07-23 | NEeFileTypes | NeSchIIIMinOthTaxType | Renamed element S3Fed4972LumpSumDistributions to S3Fed4972LumpSumDistrAmt | Nebraska - standards update | Done | This was a change to meet new naming standards because the complex type was being updated anyway.
99 | 2014V1.0 | 2014-07-23 | NEeFileTypes | NeSchIIIMinOthTaxType | Renamed element S3Fed5329EarlyDistributions to S3Fed5329EarlyDistributionsAmt | Nebraska - standards update | Done | This was a change to meet new naming standards because the complex type was being updated anyway.
100 | 2014V1.0 | 2014-07-23 | NEeFileTypes | NeSchIIIMinOthTaxType | Renamed element S3OtherTaxSubtotal to S3OtherTaxSubtotalAmt | Nebraska - standards update | Done | This was a change to meet new naming standards because the complex type was being updated anyway.
101 | 2014V1.0 | 2014-07-23 | NEeFileTypes | NeSchIIIMinOthTaxType | Renamed element SubtotalMultipliedBy296 to SubtotalMultipliedBy296Amt | Nebraska - standards update | Done | This was a change to meet new naming standards because the complex type was being updated anyway.
102 | 2014V1.0 | 2014-07-24 | NEeFileTypes | NeF3800nRenewableTaxCreditType | Deleted element KilowattHoursZeroEmission from Form 3800N | Nebraska - form change | Done | This change was a result of expired legislation.
103 | 2014V1.0 | 2014-07-25 | NEeFileTypes | Ne3800NCredType | Created new type to identify specific incentive credit claimed | Nebraska - form change | Done | Form K-1N change.
104 | 2014V1.0 | 2014-07-25 | NEeFileTypes | NeIncTaxWithheldType | Created a New Complex Type (NeIncTaxWithheldType) to identify the source of Nebraska withholding. | Nebraska - form change | Done | Form 1040N change.
105 | 2014V1.0 | 2014-07-25 | NEeFileTypes | NeFCDNCreditsReceivedType | Changed element TypeOfReceiver to be required. | Nebraska - enhancement | Done | Schema change.
106 | 2014V1.0 | 2014-07-25 | NEeFileTypes | NeFCDNCreditsReceivedType | Changed element ShareOfCredit to be required. | Nebraska - enhancement | Done | Schema change.
107 | 2014V1.0 | 2014-08-15 | NEeFileTypes | NeNOLYearAndLossType | Removed NeNOLYearAndLossType from NOL Schema. | Nebraska - form change | Done | Form Change
108 | 2014V1.0 | 2014-08-15 | IndividualStateEnumerations | NeTypeOfIncentiveProgramType | Changed enumerated list value 'Employment and Investment Growth Act (LB 775)' to '775'. | Nebraska - form change | Done | Form Change
108 | 2014V1.0 | 2014-08-15 | IndividualStateEnumerations | NeTypeOfIncentiveProgramType | Changed enumerated list value 'Nebraska Renewable Energy Tax Credit' to 'RE'. | Nebraska - form change | Done | Form Change
109 | 2014V1.0 | 2014-08-15 | IndividualStateEnumerations | NeTypeOfIncentiveProgramType | Changed enumerated list value 'Nebraska Advantage Act (LB 312)' to '312'. | Nebraska - form change | Done | Form Change
110 | 2014V1.0 | 2014-08-15 | IndividualStateEnumerations | NeTypeOfIncentiveProgramType | Changed enumerated list value 'Nebraska Advantage Rural Development Act (LB 608)' to 'NARDA'. | Nebraska - form change | Done | Form Change
111 | 2014V1.0 | 2014-08-15 | IndividualStateEnumerations | NeTypeOfIncentiveProgramType | Changed enumerated list value 'Nebraska Advantage Research and Development Act' to 'RD'. | Nebraska - form change | Done | Form Change
112 | 2014V1.0 | 2014-08-15 | IndividualStateEnumerations | NeTypeOfIncentiveProgramType | Changed enumerated list value 'Biodiesel Facility Credit' to 'BF'. | Nebraska - form change | Done | Form Change
113 | 2014V1.0 | 2014-08-15 | IndividualStateEnumerations | NeTypeOfIncentiveProgramType | Added new enumerated list value 'NMTC' for the New Markets Job Growth Investment Act credit. | Nebraska - form change | Done | Form Change
114 | 2014V1.0 | 2014-08-26 | NEeFileTypes | NeS3PartYrCreditsType | Removed this type | Nebraska - form change | Done | Schedule III.
115 | 2014V1.0 | 2014-09-05 | NEeFileTypes | NeF1040NTaxAfterNonrefCrType | Removed FederalTaxUsedIndicator element from this type. | Nebraska enhancement | Done | Schema change.
116 | 2014V1.0 | 2014-09-09 | NEeFileTypes | NeRelationToEmplType | Removed Other from the enumerated list for this type | Nebraska - form change | Done | Form Change
117 | 2015V1.0 | 2015-06-15 | IndividualStateEnumerations | NeLocalCodeType | Added enumeration value "036" for Jursidiction Battle Creek | Nebraska - tax rate change | Done | Tax Rate Change
118 | 2015V1.0 | 2015-06-15 | IndividualStateEnumerations | NeLocalCodeType | Added enumeration value "049" for Jursidiction Benedict | Nebraska - tax rate change | Done | Tax Rate Change
119 | 2015V1.0 | 2015-06-15 | IndividualStateEnumerations | NeLocalCodeType | Added enumeration value "086" for Jursidiction Callaway | Nebraska - tax rate change | Done | Tax Rate Change
120 | 2015V1.0 | 2015-06-15 | IndividualStateEnumerations | NeLocalCodeType | Added enumeration value "922" for Jursidiction Dakota County | Nebraska - tax rate change | Done | Tax Rate Change
121 | 2015V1.0 | 2015-06-15 | IndividualStateEnumerations | NeLocalCodeType | Added enumeration value "141" for Jursidiction Decatur | Nebraska - tax rate change | Done | Tax Rate Change
122 | 2015V1.0 | 2015-06-15 | IndividualStateEnumerations | NeLocalCodeType | Added enumeration value "170" for Jursidiction Elwood | Nebraska - tax rate change | Done | Tax Rate Change
123 | 2015V1.0 | 2015-06-15 | IndividualStateEnumerations | NeLocalCodeType | Added enumeration value "456" for Jursidiction Stanton | Nebraska - tax rate change | Done | Tax Rate Change
124 | 2015V1.0 | 2015-06-15 | IndividualStateEnumerations | NeLocalCodeType | Added enumeration value "495" for Jursidiction Upland | Nebraska - tax rate change | Done | Tax Rate Change
125 | 2015V1.0 | 2015-06-15 | IndividualStateEnumerations | NeLocalCodeType | Added enumeration value "496" for Jursidiction Utica | Nebraska - tax rate change | Done | Tax Rate Change
126 | 2015V1.0 | 2015-06-15 | IndividualStateEnumerations | NeRelationToEmployIIType | Added new enumeration for Form 4797N Part II. | Nebraska - enhancement | Done | Schema change.
127 | 2015V1.0 | 2015-07-08 | NEeFileTypes | Ne3800NCredType | Added NEHistoricTaxCreditAmt element to type | Nebraska - form change | Done | Form Change
128 | 2015V1.0 | 2015-07-15 | IndividualStateEnumerations | NeTypeOfIncentiveProgramType | Added enumeration value "NHTC" for the Nebraska Historic Tax Credit | Nebraska - form change | Done | Legislative change - Form change.
129 | 2015V1.0 | 2015-07-28 | NEeFileTypes | NeTransactionType | Added enumerattion list "ShortTerm Transaction" and "LongTerm Transaction" for Form 4797N | Nebraska - form change | Done | Form Change
130 | 2015V1.0 | 2015-09-14 | NEeFileTypes | NeExtraordinaryDivCalcType | Added type NeExtraordinaryDivCalcType | Nebraska enhancement | Done | Schema change.
131 | 2016V0.1 | 2016-07-14 | IndividualStateEnumerations | NEStateType | Added type NEStateType for use with NESchedule II | Nebraska enhancement | Done | Schedule II
132 | 2016V0.1 | 2016-07-20 | IndividualStateEnumerations | NeLocalCodeType | Added enumeration value "047" for Jursidiction Bellwood | Nebraska - tax rate change | Done | Tax Rate Change
133 | 2016V0.1 | 2016-07-20 | IndividualStateEnumerations | NeLocalCodeType | Added enumeration value "279" for Jursidiction Leigh | Nebraska - tax rate change | Done | Tax Rate Change
134 | 2016V0.1 | 2016-07-20 | IndividualStateEnumerations | NeLocalCodeType | Added enumeration value "533" for Jursidiction Woodriver | Nebraska - tax rate change | Done | Tax Rate Change
135 | 2016V1.0 | 2016-10-03 | Form3800NCredit | TotalRenewableEnergyTaxCredit | Allowed for 15 occurences of worksheet | Nebraska enhancement | Done | Schema change.
136 | 2017V0.1 | 2017-06-26 | IndividualStateEnumerations | NeHighSchoolDistrictCodesType | Removed enumration value "0808036" for Lynch 36 | Nebraska - school district merge | Done | School District Merger
137 | 2017V0.1 | 2017-06-26 | IndividualStateEnumerations | NeHighSchoolDistrictCodesType | Removed enumration value "0808050" for West Boyd 50 | Nebraska - school district merge | Done | School District Merger
138 | 2017V0.1 | 2017-06-26 | IndividualStateEnumerations | NeHighSchoolDistrictCodesType | Added enumration value "0808051" for Boyd county 51 | Nebraska - school district merge | Done | School District Merger
139 | 2017V0.1 | 2017-06-26 | IndividualStateEnumerations | NeHighSchoolDistrictCodesType | Removed enumration value "4508036" for Lynch 36 | Nebraska - school district merge | Done | School District Merger
140 | 2017V0.1 | 2017-06-26 | IndividualStateEnumerations | NeHighSchoolDistrictCodesType | Removed enumration value "4508050" for West Boyd 50 | Nebraska - school district merge | Done | School District Merger
141 | 2017V0.1 | 2017-06-26 | IndividualStateEnumerations | NeHighSchoolDistrictCodesType | Added enumration value "4508051" for Boyd county 51 | Nebraska - school district merge | Done | School District Merger
142 | 2017V0.1 | 2017-06-26 | IndividualStateEnumerations | NeHighSchoolDistrictCodesType | Removed enumration value "5408036" for Lynch 36 | Nebraska - school district merge | Done | School District Merger
143 | 2017V0.1 | 2017-06-26 | IndividualStateEnumerations | NeHighSchoolDistrictCodesType | Added enumration value "5408051" for Boyd county 51 | Nebraska - school district merge | Done | School District Merger
144 | 2017V0.1 | 2017-07-06 | IndividualStateEnumerations | NeLocalCodeType | Added enumeration value "041" for Jursidiction Beaver Crossing | Nebraska - tax rate change | Done | Tax Rate Change
145 | 2017V0.1 | 2017-07-06 | IndividualStateEnumerations | NeLocalCodeType | Added enumeration value "102" for Jursidiction Clarkson | Nebraska - tax rate change | Done | Tax Rate Change
146 | 2017V0.1 | 2017-07-06 | IndividualStateEnumerations | NeLocalCodeType | Added enumeration value "162" for Jursidiction Edison | Nebraska - tax rate change | Done | Tax Rate Change
147 | 2017V0.1 | 2017-07-06 | IndividualStateEnumerations | NeLocalCodeType | Added enumeration value "188" for Jursidiction Fort Calhoun | Nebraska - tax rate change | Done | Tax Rate Change
148 | 2017V0.1 | 2017-07-06 | IndividualStateEnumerations | NeLocalCodeType | Added enumeration value "212" for Jursidiction Greeley | Nebraska - tax rate change | Done | Tax Rate Change
149 | 2017V0.1 | 2017-07-06 | IndividualStateEnumerations | NeLocalCodeType | Added enumeration value "391" for Jursidiction Pilger | Nebraska - tax rate change | Done | Tax Rate Change
150 | 2017V0.1 | 2017-07-06 | IndividualStateEnumerations | NeLocalCodeType | Added enumeration value "277" for Jursidiction Lawrence | Nebraska - tax rate change | Done | Tax Rate Change
151 | 2017V0.1 | 2017-07-06 | IndividualStateEnumerations | NeLocalCodeType | Added enumeration value "317" for Jursidiction Meadow Grove | Nebraska - tax rate change | Done | Tax Rate Change
152 | 2017V0.1 | 2017-07-20 | IndividualStateEnumerations | NESchoolReadinessStaffAmtType | Added new enumeration for 1040N element SchoolReadinessStaffMemCredAmt | Nebraska legislative change | Done | Legislative change - Form change.
153 | 2017V0.1 | 2017-07-21 | NEeFileTypes | SchTANFType | Added SchTANFType to capture data for TANF credit. | Nebraska legislative change | Done | Legislative change - Form change.
154 | 2017V0.1 | 2017-08-03 | NEeFileTypes | EligibleEmployeeType | Added EligibleEmployeeType to NEeFileTypes | Nebraska legislative change | Done | Legislative change - Form change.
155 | 2017V0.1 | 2017-08-14 | NEeFileTypes | NeK1NEntityType | Modified type to remove duplicate elements | Nebraska Schema Change | Done | Schema change.
156 | 2017V1.0 | 9/21/20117 | IndividualStateEnumerations | NESchoolReadinessStaffAmtType | Added enumaration value "1000" for Married filing joint taxpayers | Nebraska Schema Change | Done | Schema change.
157 | 2017V1.0 | 9/21/20117 | IndividualStateEnumerations | NESchoolReadinessStaffAmtType | Added enumaration value "2500" for Married filing joint taxpayers | Nebraska Schema Change | Done | Schema change.
158 | 2017V1.0 | 9/21/20117 | IndividualStateEnumerations | NESchoolReadinessStaffAmtType | Added enumaration value "3000" for Married filing joint taxpayers | Nebraska Schema Change | Done | Schema change.
159 | 2017V2.0 | 2017-10-24 | IndividualStateEnumerations | NESchoolReadinessStaffAmtType | Added enumeration vales "1750, 2250 & 2750" for Married filing joint taxpayers. | Nebraska Schema Change | Done | Schema change.
160 | 2017V2.0 | 2017-11-03 | IndividualStateEnumerations | NEVolunteerEmerRespCredAmtType | NEVolunteerEmerRespCredAmtType - enumerated list for VolunteerEmerRespCredAmt | Nebraska legislative change | Done | Schema change.
161 | 2018V0.1 | 2018-07-27 | NEeFileTypes | FormTANFType | Added FormTANFType to capture data for TANF credit. | Nebraska - form change | Done | Schema change.
162 | 2018V0.1 | 2018-07-27 | NEeFileTypes | SchTANFType | Deleted SchTANFType. | Nebraska - form change | Done | Schema change.
163 | 2018V0.1 | 2018-07-27 | NEeFileTypes | NeS3ComputedNebraskaTaxType | Deleted AdditionalTaxRtScheduleTaxAmt element from type | Nebraska - form change | Done | Schema change.
164 | 2018V0.1 | 2018-07-27 | NEeFileTypes | NeS3ComputedNebraskaTaxType | Deleted SubtotalScheduleIIITaxAmt element from type | Nebraska - form change | Done | Schema change.
165 | 2018V0.1 | 2018-08-22 | IndividualStateEnumerations | NeHighSchoolDistrictCodesType | Deleted enumeration value "1490017" | Nebraska - school district merge | Done | School District Merger
166 | 2018V0.1 | 2018-08-27 | NEIndividualEFileTypes | NEF1040nPersonalExemptionType | Added NeF1040nPersonalExemptionType to capture the number of exemptions on Form 1040N. | Nebraska legislative change | Done | Schema change.
167 | 2018V0.1 | 2018-08-27 | IndividualStateEnumerations | NeNumPersonalExemptionType | Added enumeration NeNumPersonalExemptionType | Nebraska - schema change | Done | Legislative change - Form change.
168 | 2018V0.1 | 2018-08-30 | IndividualStateEnumerations | NeQualifiedCareAmountType | Added enumeration NeQualifiedCareAmountType for Form 2441N | Nebraska - schema change | Done | Schema change.
169 | 2018V0.1 | 2018-08-30 | IndividualStateEnumerations | NeSpecifiedAmountType | Added enumeration NeSpecifiedAmountType for Form 2441N | Nebraska - schema change | Done | Schema change.
170 | 2018V0.1 | 2018-09-04 | IndividualStateEnumerations | NeTypeOfIncentiveProgramType | Deleted enumeration value "BF" | Nebraska legislative change | Done | Legislative change - Form change.
171 | 2018V1.1 | 2018-11-02 | NEeFileTypes | NEDecimalType | Modified total digits from 7 to 8 to match example | Nebraska Schema Change | Done | Schema change.
172 | 2018V1.1 | 2018-11-05 | IndividualStateEnumerations | NeLocalCodeType | Removed enumration value "437" for Shelton | Nebraska - tax rate change | Done | Tax Rate Change
173 | 2018V1.2 | 2019-01-15 | IndividualStateEnumerations | NESchoolReadinessStaffAmtType | Enumerated values were updated for ty 2018. | Nebraska legislative change | Done | Schema change.