## Sheet1
[5 empty] | Estimate Based on 3 Year Average |  |  | Estimate Based on Prior Year (2024) |  |  | Estimate Based on Team Feedback |  |  |  | Estimate Based on SMB/Team Feedback |  |  |  |  | 2025 V. 2024 AS OF JUNE 30
PROJECT | 2022 TOTAL | 2023 TOTAL | 2024 TOTAL | 3 Year Average (projected 2025 Total) | AS OF JUNE 30, 2025 | Projected Hours (July-Dec 2025) | Total (Hrs as of June 30,2025+projected hrs. July-Dec.) | AS OF JUNE 30, 2025 | Projected Hours (July-Dec 2025) | Total (Hrs as of June 30,2025+projected hrs. July-Dec.) | AS OF JUNE 30, 2025 | Projected Hours (July-Dec 2025) | Total (Hrs as of June 30,2025 +projected hrs. July-Dec.) | PROJECT |  | As of SEPT. 20, 2025 | % of Projected thru Dec. 2025 | Total Projected Hours thru Dec. 31, 2025 (Jan-Dec 2025) | % of BUDGET (26,300 hrs.) | AS OF JUNE 30, 2025 | AS OF JUNE 30,2024
(Major) | [13 empty] | (Major)
PORTFOLIOS (IRs & FRs ONLY) | 4773.5 | 10897.05 | 9286 | 8318.85 | 3415.75 | 4903.1 | 8318.85 | 3416 | 5870 | 9286 | 3416 | 6676 | 10092 | PORTFOLIOS (IRs & FRs ONLY) |  | 4922.75 | 56.2214 | 8756 |  | 3416 | 6070
INTERNATIONAL FORMS | 1189.75 | 2603 | 2923.5 | 2238.75 | 1600.25 | 638.5 | 2238.75 | 1600 | 1323.5 | 2923.5 | 1600 | 1500 | 3100 | INTERNATIONAL FORMS |  | 2483.75 | 80.121 | 3100 |  | 1600 | 1494
PROPERTY TAX NAVIGATORS (PRTN) | 2693.55 | 4802.75 | 2446.75 | 3314.35 | 872.75 | 2441.6 | 3314.35 | 873 | 1573.75 | 2446.75 | 873 | 1727 | 2600 | PROPERTY TAX NAVIGATORS (PRTN) |  | 1546.25 | 96.6406 | 1600 |  | 873 | 1942
TAXBOOK | 198.58 | 513 | 1265 | 658.86 | 110 | 548.86 | 658.86 | 110 | 1155 | 1265 | 110 | 809 | 919 | TAXBOOK |  | 110 | 11.9695 | 919 |  | 110 | 653
IRC CODE UPDATE | [5 empty] | 100 | 100 |  | 100 | 100 |  | 100 | 100 | IRC CODE UPDATE |  | 56.25 | 56.25 | 100
FORMS (POC) |  |  |  |  | 640 |  | 640 | 640 |  | 640 | 640 |  | 640 | FORMS (POC) |  | 640 | 100 | 640 |  | 640
FORMS (Projected) (projected through remaining of the year) | [5 empty] | 1500 | 1500 |  | 1500 | 1500 |  | 1500 | 1500 | FORMS (Projected) (projected through remaining of the year) |  | 584 | 38.9333 | 1500
BLAWBooks |  |  |  |  | 571.25 | 1652 | 2223.25 | 571.25 | 1652 | 2223.25 | 571.25 | 1652 | 2223.25 | BLAWBooks |  | 649.25 | 29.206 | 2223 |  | 571.25
TOTAL MAJOR PROJECTS | 8855.38 | 18815.8 | 15921.25 | 14530.81 | 7210 | 11784.06 | 18994.06 | 7210.25 | 13174.25 | 20384.5 | 7210.25 | 13964 | 21174.25 | TOTAL MAJOR PROJECTS |  | 10992.25 | 58.3515 | 18838 |  | 7210.25 | 10159
Other Projects (Non-Major) | 1978.98 | 4522.25 | 3005.75 | 3168.9933 | 1367 | 1801.9933 | 3168.9933 | 1366.75 | 3006 | 4372.75 | 1366.75 | 3006 | 4372.75 | Other Projects (Non-Major) |  | 1851 | 42.3279 | 4373 |  | 1366.75 | 1982
YEARLY TOTAL | 10834.36 | 23338.05 | 18927 | 17699.8033 | 8577 | 13586.0533 | 22163.0533 | 8577 | 16180.25 | 24757.25 | 8577 | 16970 | 25547 | YEARLY TOTAL |  | 12843.25 | 55.3326 | 23211 |  | 8577 | 12141
[16 empty] | 12843.25 | 48.8337 | 26300
[7 empty] | Estimate Based on 3 Year Average |  |  | Estimate Based on Prior Year (2024) |  |  | Estimate Based on Team Feedback
Budget | [6 empty] | 26300 |  |  | 26300 |  |  | 26300 |  |  |  |  | 26300
less Projected Hours (Jan.- Dec. 2025) | [6 empty] | 22163 |  |  | 24757 |  |  | 25547 |  |  |  |  | 23211 | 88.2548
Projected Budget Savings/Overrun | [6 empty] | 4137 |  |  | 1543 |  |  | 753 |  |  |  |  | 3089 | 13.3083
NOTES: TEAM SUGGESTED FIGURES
Portfolio- 2 year Ave. (2023,2024)
International Forms- Previous Year+300 hrs due to additional QA Task
PRTN -Previous year +200 hrs due to Big Beautiful Bill Changes
Tax Book - Average of 2023 & 2024 due to caryover charges