## Slide 1: 2024 TPQA/Forms
Summer (and beyond) Projects

## Slide 3: Summer Hiatus for current scrum teams Production, Content Oversight, Forms
Summer Focus on Projects, Cross-Training, and Learning
What does this look like?

## Slide 4
Calcs
Documentation
Calc tool conversion
Deliverable: Deliver POC training and ensure effective learning to identified Innodata team members | 
Project Lead | Key Team Members
Bob | Kevin
Contributors | Sarah
Key Dates | 
Start date: | Key Milestones/dates
5/1/2024 | [Training docs ready] MAY24 [POC Kickoff] MAY28 [Complete Training] JUN10 [Complete POC test] JUN17 [Discuss Results] JUN21 [Continue training – contingent upon results] JUN24 TBD
Completion | 
7/1/2024 (POC) 9/1/2024 (cont'd training) | 
Deliverable: Useable Calc Tools converted to web-based application | 
Project Lead | Key Team Members
Kevin | Bob Mark
Contributors | 
Key Dates | 
Start date: | Key Milestones/dates
4/5/2024 | [Create user stories] MAY24 [Top 3 tools tested and live] JUL31 [Top 5 tools tested and live] SEP30 [Remaining tools scheduled in sprints] DEC31
Completion | 
12/31/2024 | 
Deliverable: Provide updated and useable Work instructions for the Calc Process operation | 
Project Lead | Key Team Members
Bob & Kevin | 
Contributors | Sarah, Carolyn, Ricky
Key Dates | 
Start date: | Key Milestones/dates
4/5/2024 | [Flowchart updated] MAY14 [Current WI revisions] MAY17 [WIs tested and finalized] MAY23 [WIs maintained to match tool conversion] within 1 week after tool release
Completion | 
6/1/2024 | 
Calcs Project Owner: Sarah
Training
Refresher (internal team)
Innodata
Workflow assessment
Deliverable: Report of hours, team, and distribution of time in Calcs in 2023 season; plan for reduction in hours and distribution of Calcs hours across more people in 2024 season. | 
Project Lead | Key Team Members
Carolyn | Sarah
Contributors | Justyna?
Key Dates | 
Start date: | Key Milestones/dates
##/##/2024 | [create query & gather initial data] JUN28 [Analyze 2023-24 data] JUL12 [Create a plan to distribute for 2024-25] AUG9
Completion | 
9/1/2024 | 
Scrum team:
Bob
Carolyn
Sarah
Ricky/Justyna?
As needed, keep in loop:
Mark, Joe A
Calcs
Scrum Master: Kevin

## Slide 5
Systems and Process
Drive & Server (google migration)
Workflow Enhancements/Fixes
Sys/Proc Project Owner: Carolyn
STF to BTAX Publishing Mastery
Deliverable: Updated STF VDI template, including new software versions for Website Watcher, Acrobat, Enfocus, SuperBoxing | 
Project Lead | Key Team Members
Raymond Wong | Sherry
Contributors | Sarah, Carolyn
Key Dates | 
Start date: | Key Milestones/dates
##/##/2024 | [Update STF VDI template with all new programs] JUN1 [Test VDI rollout] [Rollout VDIs] MMM/DD [Adjust program settings for Acrobat]
Completion | 
##/##/2024 | 
Deliverable: Useable documentation migrated to SharePoint | 
Project Lead | Key Team Members
Carolyn | Sarah Sherry Mark
Contributors | Ramkumar Raghavan
Key Dates | 
Start date: | Key Milestones/dates
4/1/2024 | -Cleanup shared drives MAY17 -Copy/transfer shared to personal, adjust permissions MAY30 Migrate to Sharepoint JUN3 Adjust Workflow login authentication] -Manually recreate flowcharts MMM/DD -Manually adjust WI TOC links -Manually update links/formatting within Work instructions Test stfprdw-apps902 migrated files
Completion | 
12/31/2024 | 
Software Updates
Deliverable: Released Workflow Enhancements | 
Project Lead | Contributors
Sherry | Carolyn, Candice, Annette, Mark
Key Dates | 
Start date: | Key Milestones/dates
5/1/2024 | [Write user stories/wish list] JUN3 [Discuss & finalize with Mad Tax] JUN17 [Test/give feedback] As stories are released [Release to production] As time allows
Completion | 
12/1/2024 | 
Deliverable: Substantive understanding and basic documentation of steps/processes between STF Forms release and publishing on BTAX; ability to identify source of and/or actively participate in identifying resolution to problems publishing Forms to BTAX. |  | 
Project Lead | Key Team Members | 
Carolyn | Sarah Sherry | Jason
Contributors | Sally, Beach, Raymond, | 
Key Dates | 
Start date: | Key Milestones/dates
5/1/2024 | [Gather and analyze existing documentation] MMM/DD [Meet with respective teams to fill in gaps in process] MMM/DD [final review with all units] MMM/DD
Completion | 
11/30/2024 | 
Scrum team:
Carolyn
Sarah
Raymond
Kidus
Jason
Sherry
As needed, keep in loop:
Mark, Joe A, Greg Cashel, Emily, Beach Wires
Documentation updates
Deliverable: Updated documentation to reflect process changes of 2024 | 
Project Lead | Key Team Members
Jessica | Sherry, DASes
Key Dates | 
Start date: | Key Milestones/dates
7/1/2024 | [Remove PwC] [Question Operation] [Acquisition rewrite] [Approvals updates] [Quick Guides]
Completion | 
10/30/2024 | 
Systems and Process
Scrum Master: Sherry

## Slide 6
Acquisition
Acquisition Project Owner: Kenya
“Team Acquisition” POC Design and Implementation
Jx Redistribution
Jx Updates
Deliverables: Jx Pages. Updated and consistent jurisdiction information pages Calendar of State Deadlines/busy periods | 
Project Lead | Key Team Members
Tan | Candice, Jessica
Anticipated Contributors | DASes
Key Dates | 
Start date: | Key Milestones/dates
5/1/2024 | Determine standard format MAY31 Verify correct links for all JXs JUN14 Create Approval Deadline Calendar Update each page format, links, info SEP16
Completion | 
8/1/2024 | 
Lead: Jason
Start date: 5/16/2024
Completion: ##/##/2024
Deliverable: Forms Acquisition team POC running thru 2024 forms season | 
Project Leads | Key Team Members
Annette (Technical) Kenya (Execution) | Annette Ricky M. Cassandra
Anticipated Contributors | DASes, Donna, Kidus
Acquisition Training
Key Dates | 
Start date: | Key Milestones/dates
05/01/2024 | [Name the new team] ASAP [Determine /request preliminary code, access changes, etc. Prep Teams] 05/23 Rollout Phase] 06/03 [Begin Evaluation 12/01
Completion | 
10/31/2024 | 
Key Milestones/dates
MadTax dependencies [milestone 2] MMM/DD [milestone 3] MMM/DD
Usage Data/ Evaluation
Scrum team:
Annette
Kenya
Ammanuel
POC team (Ricky M., Cassandra, Donna)
Justyna
Jason
As needed, keep in loop:
Mark, Joe A, STF DAS team,
Project Manager: Annette
Deliverable: Usage data from Amplitude from which actionable decisions can be made regarding forms to discontinue/carry as PDF-only | 
Project Leads | Key Team Members
Ammanuel and Carolyn | Annette
Contributors | 
Acquisition
Scrum Master: Sarah
Key Dates | 
Start date: | Key Milestones/dates
5/13/2024 | [Meet/gather data] MAY24 [Draft distro list] JUN7 [Final Distro List] JUN14
Completion | 
6/14/2024 | 

## Slide 7
Metrics
Vendor Efficiency
Project Owner: Sally
Project Lead | Key Team Members
Ricky C | Sarah Cassandra Sally
Contributors | Murat, Shawne
Project Manager: Ricky C
Scrum team:
Sally
Ammanuel
Ricky
Sarah
Justyna
As needed: Shawne, Kenya, Carolyn, Cassandra
Deliverable: Improved Infocon workflows, evidenced with measurable reductions in vendor hours spent per task. | 
Dates | 
Key Milestones/dates | 
Portfolio “enter edits” workflow MMM/DD [milestone 2] MMM/DD [milestone 3] MMM/DD | 
Workflow changes
Deliverable: Transition TPQA conversion and updating tasks to Innodata, utilizing available capacity, evidenced via data dashboard | 
Key Dates | 
Key Milestones/dates | 
[POC begins] MAY 21 GTG/VAT ongoing. MMM/DD PRTN enter edits. MMM/DD Standardized QA. MMM/DD | 
Innodata: New work
Deliverable: Proof of concept, “scoring” of Word redline files to enable tighter oversight of vendor time | 
Key Dates | 
 | Key Milestones/dates
 | [milestone 1] MMM/DD [milestone 2] MMM/DD [milestone 3] MMM/DD
Task Scoring Benchmarks
Deliverable: Jira TPQA dashboard providing transparency into staff time allocations on TPQA-tracked tasks | 
Project Lead | Key Team Members
Justyna | Shawne Kenya Carolyn Ammanuel
Contributors | 
Scrum Dashboards
Project Manager: Ammanuel
Key Milestones/dates
[milestone 1] June/30 [milestone 2] July/31 [milestone 3] MMM/DD
TPQA revised (jira data)
Key Dates | 
Start date: | Key Milestones/dates
##/##/2024 | [milestone 1] June/30 [milestone 2] July/31 [milestone 3] MMM/DD
Completion | 
##/##/2024 | 
Deliverable: Dashboard providing transparency into staff time allocations on TPQA and Forms work | 
Project Leads | Key Team Members
Justyna, Sarah | 
Contributors | 
Combined TPQA/Forms (jira + workflow data)
Vendor dashboard
Deliverable: Vendor dashboard, showing utilization of Innodata and Infocon time, by project. | 
Project Lead | Key Team Members
Sarah | Ricky Sally
Contributors | 
Metrics
Scrum Master: Sarah

## Slide 8
Portfolio Workflow revamp/ overhaul
Deliverable(s): Deliver training to diversify and broaden skills and experience for more flexibility during peak seasons. General Cross-Training (Oxygen, BWIP, etc) Composing Portfolios (PDF output) Exporting Portfolios from BWIP |  | 
Project Lead | Key Team Members | 
Candice | Murat Jason Ricky C Ricky M | Kidus Jessica Sarah
Key Dates | 
Start date: | Key Milestones/dates
05/17/2024 | QA for Print JUN 3 and JUN 5 (Done) Anthology JUN 11 (Done) BWIP/Oxygen JUN 17 and JUN 18 Composition JUN ?? Export Training JUN ??
Completion | 
08/30/2024 | 
Portfolio Project Owner: Shawne
Training
Composing
Master Portfolio spreadsheet (excel)
Cross-Training
Exporting
Productionize New Print Workflows
Deliverable: Transition “new” print workflows into ongoing workflows assigned to individuals with areas of responsibility/documnetation | 
Project Lead | Key Team Members
Shawne | Sally Murat Ricky
Deliverable: Single spreadsheet containing key facts about all portfolios | 
Project Lead | Team Members
Shawne | Murat Sally
Deliverable: Jira dashboard showing status of all phases of portfolio production activities: Exports for authors Production (including obsol cites, BNA Picks) Print | 
Project Lead | Key Team Members
Ricky C | Shawne Murat Jessica
Anticipated Contributors | Pete Larry
Key Dates | 
Start date: | Key Milestones/dates
##/##/2024 | [milestone 1] MMM/DD [milestone 2] MMM/DD [milestone 3] MMM/DD
Completion | 
##/##/2024 | 
Scrum team:
Shawne
Murat
Ricky C.
Ricky M.
Sally
Candice
Jason
Jessica
Kidus
Paula
Tan
As needed: Pete
Key Dates | 
Start date: | 4/15/2024
Completion | 8/30/2024
Portfolio Workflow Revamp
Refactor Obsolete Cites Workflow
Deliverable: Overhaul Obsolete Cites workflow to reduce hours and expedite completion | 
Project Lead | Team
Paula | Tan
Consolidated Portfolio Dashboard (in Jira)
Key Dates | 
Start date: | Key Milestones/dates
6/1/2024 | [Requirements document] June 1 [Beta version] June 30 [Final version] 8/25/2024
Completion | 
8/15/2024 | 
Key Dates | 
Start date: | Key Milestones/dates
?? | [???] MMM/DD [???] MMM/DD [???] MMM/DD
Completion | 
?? | 
Scrum Master: Ammanuel

## Slide 9
 |  | Scrum Teams |  |  |  |  |  |  |  | 
 | PROJECT OWNER/ Lead | Scrum Team |  |  |  | Occasional participant |  |  |  | Scrum Master
Shawne | PORTFOLIO OVERHAUL Print Workflow, Master Portfolio | P |  |  |  | M |  |  |  | 
Murat |  | P |  |  |  |  |  |  |  | 
Cassandra |  | A |  |  |  | M |  |  |  | 
Jason | Jx redistrib | A | S |  |  | P |  |  |  | 
Candice | Comp training | A | P |  |  |  |  |  |  | 
Carolyn | SYSTEM & PROCESS Drive & Server, Workflow Assessment, STF to BTAX mastery, Content Evaluation | S | C |  |  | M | A |  |  | 
Sherry | Workflow Enhancements | S |  |  |  |  |  |  |  | Systems/Proc
Sarah | CALCS Vendor dashboard, TPQA/Forms dashboard | S | M | C |  |  |  |  |  | Acquisition, Metrics
Annette | Team Acquisition POC | A |  |  |  |  |  |  |  | 
Kevin | Calc tool conversion, Calcs Wis | C |  |  |  |  |  |  |  | Calcs
Bob | Calc Training, Calcs Wis | C |  |  |  |  |  |  |  | 
Jessica | Documentation Updates, | P | A |  |  | S |  |  |  | 
Kenya | ACQUISITION | A |  |  |  | M |  |  |  | 
Tan | Jx page update | A | P |  |  |  |  |  |  | 
Paula | Refactor Obsolete Cites Workflow | P |  |  |  |  |  |  |  | 
Donna |  | A |  |  |  |  |  |  |  | 
Ammanuel | Scrum Dashboards | A | M |  |  |  |  |  |  | Portfolios
Justyna | TPQA dashboard, TPQA/Forms dashboard | M | A |  |  |  |  |  |  | 
Ricky M |  | A |  |  |  | P |  |  |  | 
Kidus |  | A | S |  |  | P |  |  |  | 
Sally | METRICS | A | M |  |  | P | S |  |  | 
Raymond | Software Updates | S |  |  |  |  |  |  |  | 
Ricky C | Vendor Efficiency | M | P |  |  |  |  |  |  | 
LEGEND |  | 
A | ACQUISITION | Kenya
C | CALCS | Sarah
M | METRICS | Sally
P | PORTFOLIOS OVERHAUL | Shawne
S | SYSTEMS & PROCESS | Carolyn

## Slide 10
Mon | Tues | Wed | Thurs | Fri
Scrum masters/ Project Owner/leads meeting Review: Last week -- “done” This week – “to do” Any critical path obstacles? Challenges/Wins Team performance overall other | Daily Stand-up Calcs Systems & Process Acquisition Metrics Portfolio Overhaul | Daily Stand-up Calcs Systems & Process Acquisition Metrics Portfolio Overhaul | Daily Stand-up Calcs Systems & Process Acquisition Metrics Portfolio Overhaul | 
All Five Team Retrospectives and/or Sprint Reviews (TBD) |  |  |  | 
June 3 – August 30
September….
Reconfigure scrum teams going forward based upon what we learn over the summer

## Slide 11: Next Steps
Scrum masters
  Week of May 27
 | Project Owners | Scrum Masters | Team members
Week of May 20 (i.e., next week) | Meet with project managers/ leads, review: project scope, deliverables critical milestones, dates obstacles | CSM training Meet with your product owner and project managers/leads Expectations Jira team tracking Schedule kick-off meeting | Review team assignment(s) Touch base with project manager/lead: Questions? Ideas? Suggestions?
Week of May 27 | Work with Scrum Master to create team frameworks, e.g.: Project tickets Team board | Team Kickoff meeting Review scope, goals Establish team norms, meeting cadence, etc. Jira organization | 
Week of June 3 | And off we go! Daily standups: Tues-Wed-Thur |  |